



National Planning Reform Blueprint  
Northern Territory Progress Report

March 2025

© Northern Territory Government 2025

This publication is available for your use under a [Deed - Attribution 4.0 International - Creative Commons](https://creativecommons.org/licenses/by/4.0/deed.en) licence, with the exception of the Northern Territory Government, photographs, images, signatures and where otherwise stated. The full licence terms are available from <https://creativecommons.org/licenses/by/4.0/legalcode.en>.

Creative Commons attribution licence 3.0 icon. 

Use of Northern Territory Government material under a [Deed - Attribution 4.0 International - Creative Commons](https://creativecommons.org/licenses/by/4.0/deed.en) licence requires you to attribute the work (but not in any way that suggests that Northern Territory Government endorses you or your use of the work).

**Northern Territory Government material used ‘as supplied’.**

Provided you have not modified or transformed Northern Territory material in any way including, for example, by changing the Northern Territory text; calculating percentage changes; graphing or charting data; or deriving new statistics from published Northern Territory statistics — then Northern Territory prefers the following attribution:

*Source: Northern Territory Government* Department of Lands, Planning and Environment

**Derivative** **material**

If you have modified or transformed Northern Territory material, or derived new material from those of the Northern Territory Government in any way, then Northern Territory Government prefers the following attribution:

*Based on Northern Territory Government Department of Lands, Planning and Environment*

**Other uses**

Enquiries regarding this licence and any other use of this document are welcome at:

Department of Lands, Planning and Environment  
GPO Box 1680  
DARWIN NT 0801

Contents

[Measure 2 1](#_Toc176345181)

[How the Northern Territory’s strategic plan(s) will deliver on housing supply targets 1](#_Toc176345182)

[Measure 3 3](#_Toc176345183)

[Summary of planning reforms 3](#_Toc176345184)

[Summary of zoning reforms 4](#_Toc176345185)

[Summary of land release reforms 4](#_Toc176345186)

[Summary of density and other reforms 5](#_Toc176345187)

[Measure 4 6](#_Toc176345188)

[Key findings from a development ready land stocktake 6](#_Toc176345189)

[Measure 5 9](#_Toc176345190)

[Zoning, planning and other amendments to support dense, well-located housing 9](#_Toc176345191)

[Reforms to non-planning barriers preventing a diversity of housing 11](#_Toc176345192)

[Measure 6 12](#_Toc176345193)

[Identifying barriers in development approvals 12](#_Toc176345194)

[Key barriers to the timely issuing of development approvals 12](#_Toc176345195)

[Barriers to delivering housing where development approvals have been granted 12](#_Toc176345196)

[Reforms to development approvals 12](#_Toc176345197)

[Reforms to social and affordable housing approval pathways 12](#_Toc176345198)

[Reforms addressing barriers to the timely issuing of development approvals 13](#_Toc176345199)

[Planning reforms to address existing development approvals which have not been acted upon 13](#_Toc176345200)

[The Northern Territory’s position on planning and inclusionary zoning reforms to support permanent affordable, social and other specialist housing in developments 14](#_Toc176345201)

[Other reforms to development approval pathways 14](#_Toc176345202)

[Initiatives to share planning data and improve visibility of factors affecting housing delivery 14](#_Toc176345203)

[Measure 10 15](#_Toc176345204)

[Well located government land suitable for housing 15](#_Toc176345205)

[Best practice examples of developing government land 17](#_Toc176345206)

[Case Study – Katherine East Urban Village Precinct 17](#_Toc176345207)

|  |
| --- |
| Measure 2 Planning Ministers will report to National Cabinet on state, regional and local strategic plans that reflect their jurisdiction’s share of housing supply targets agreed by National Cabinet and links with infrastructure pipelines. |

## How the Northern Territory’s strategic plan(s) will deliver on housing supply targets

The Northern Territory (NT) Planning Commission sets the strategic framework for integrated land use, transport and infrastructure planning and consults with the community to develop strategic plans and policies for inclusion in the NT Planning Scheme.

The NT has always had a plan for land release in place to ensure there is land supply available for entry and affordable housing products. Land use planning in the NT is done at a regional scale and is administered through a centralised (state level) planning system. Regional Land Use Plans establish an overarching regional framework to manage growth in the 4 major centres – Darwin, Katherine, Tennant Creek and Alice Springs. Each plan includes a Land Use Structure that identifies development opportunities throughout the relevant region, including locations to accommodate urban, peri-urban and rural lifestyle developments and their associated potential dwelling yields. These plans were developed by the NT Planning Commission through a 3-stage consultation process with the public and relevant government and industry stakeholders (including local government and regional bodies).

Area Plans, which give effect to regional targets, contain detail of the expected growth and potential capacity of new dwellings in each area. The number of additional dwelling/population numbers specified in the local plans are based on detailed infrastructure studies that accompany the development of these ‘local’ strategic plans. Regional and local plans in the NT have sufficient existing capacity to accommodate the agreed housing targets.

The NT’s draft Land Development Strategy is a recommendation of the Bringing Land to Market report and has been drafted to detail the forecasted pipeline of land supply in the NT’s major urban centres for residential housing over the next 20 years, based on potential dwelling yields identified in strategic land use plans.

The draft Land Development Strategy uses population projections from the NT Department of Treasury and Finance (and the ABS) and considers a low and high growth scenario based on potential economic development that forecasts higher growth, provided by the NT Department of the Chief Minister and Cabinet.

The draft Land Development Strategy forecast of land supply is aimed at providing for the sequencing of land development and in turn the timing for the delivery of district-level enabling infrastructure to support continued land supply. District-level infrastructure includes key structuring roads within districts, and power, water and sewer headworks which are identified and costed in a Land Development Program (the infrastructure program for land), generally recovered through the uplift in the value and sale of Crown land or through infrastructure contributions.

The district-level enabling infrastructure delivered by the NT Government enables land development and housing supply that could be undertaken by the private sector. In a number of remote towns, the NT Government also undertakes the land development role.

In terms of its contribution towards national housing supply targets to meet the National Housing Accord, the NT has committed to provide 11,430 homes, including 1492 social and affordable homes, over the 5-year period from 2024.

|  |
| --- |
| Measure 3 Planning Ministers will undertake planning, zoning, land release and other reforms, such as increasing density, to meet their jurisdiction’s share of housing supply targets agreed by National Cabinet. |

## Summary of planning reforms

#### Increased maximum floor area for second dwellings

*Enacted 1 December 2023| First reported in March 2024*

On 1 December 2023 an amendment to the NT Planning Scheme took effect that increased the maximum floor area of independent living units (second dwellings) allowed on single dwelling lots (without any planning approval being necessary) from 50m2 to 75m2.

This change provides for the increased utilisation of infill land for social and affordable housing purposes.

#### New design responses for mixed use developments

*Enacted 17 February 2023 | First reported in March 2024*

On 17 February 2023 an amendment to the NT Planning Scheme took effect, which amongst other changes, included incorporating design responses for mixed use development contained in strategic land use plans as development requirements within the scheme. For example, replacing set density requirements for apartments and mixed-use buildings with a significantly more flexible plot ratio.

Introduction of a residential plot ratio for medium-high density development will provide greater flexibility in design and assist with achieving greater density.

#### Extended exemption from approvals for remote subdivisions

*Enacted 3 March 2023 | First reported in March 2024*

On 3 March 2023 a time limited exemption under the *Planning Act 1999* was extended to June 2028, conditionally removing the need for subdivision approval for land development in remote communities as part of the $1.1 billion remote housing program, as long as these are supported by the community and Traditional Owners (through land tenure agreements).

This exemption provides for the fast-tracked release of land for social and affordable housing purposes.

#### Katherine Densification Policy – denser townhouses

*Enacted 7 October 2022 | First reported in March 2024*

On 7 October 2022 an amendment to the NT Planning Scheme took effect, known as the Katherine Densification Policy. This facilitates townhouse development at a density of 1 dwelling per 400m2 (rather than 1 dwelling per 800m2 as is normally the case) for standard Low Density Residential   
(Zone LR) lots in Katherine East.

This change provides for the increased utilisation of infill land for social and affordable housing purposes.

## Summary of zoning reforms

#### Area Plans - Areas for Change

*Update: In progress / First reported September 2024*

Area Plans, contained within the NT Planning Scheme, implemented in the NT’s Compact Urban Growth Policy, identify compact urban growth localities around activity centres, public transport corridors and other localities that satisfy the objective of this Policy. These localities are identified as an ‘area for change’ in an Area Plan.

Planning scheme amendments can be requested by a landowner to rezone a parcel of land in an ‘area for change’. These are progressed by the NT Government in a timely manner to facilitate increased densities, where infrastructure and amenities are available.

Investigations continue in relation to additional reforms to improve housing related outcomes.

## Summary of land release reforms

#### Bringing land to market report

*Update: In progress | First reported in March 2024 / Updated March 2025*

The NT has recently reformed the planning system to give effect to the ‘Bringing Land to Market Report’ which included 23 recommendations to achieve a titled land supply that satisfies the market demand (including for affordable housing) in a timely and efficient manner.

The Bringing Land to Market Report was commissioned by the NT Government in 2021 to identify improvements to bring titled land to the market to keep pace with Territorian’s needs. Further information and a copy of the report can be found here: <https://environment.nt.gov.au/careers-programs-publications/land-development-process-report-and-recommendations>.

Of the 23 recommendations, 15 have been implemented with the remaining recommendations recategorised into three Land Development Initiatives, which include:

* Land Development Initiative 1: Integrated Strategic Planning policy and guidelines that outline how the NT plans and delivers sufficient land supply to support population growth and economic development.
* Land Development Initiative 2: Process Improvement initiatives that require legislative amendment in order for realisation. This includes mandating subdivision development minimum standards and introduction of timeframes for service authority approvals for the design, construction and handover of public infrastructure; and
* Land Development Initiative 3: Economic Demand Forecasting that assesses demand for residential, commercial and industrial land associated with high economic growth scenarios within key industries to inform land supply planning.

## Summary of density and other reforms

Investigations are continuing in relation to further initiatives and reform mechanisms to increase densities.

|  |
| --- |
| Measure 4 Planning Ministers will identify well-located ‘development ready’ land having appropriate regard to the protection of land with key attributes e.g. environmental or economic. |

## Key findings from a development ready land stocktake[[1]](#footnote-2)

**Urban land supply***Update: In progress| First reported in March 2024 / Updated March 2025*

The NT’s draft Land Development Strategy identifies development ready land as   
‘Land Under Development’ which is land that is in the hands of developers, with reticulated infrastructure service connections to be provided through the subdivision development process to produce titled land to market in Greater Darwin, Alice Springs, Katherine and Tennant Creek.

The below table identifies:

* estimated number of lots and dwellings within Land Under Development for new development areas;
* infill opportunities identified in Area Plans that have current development approvals in place; and vacant undeveloped lots within existing developed urban centres with infrastructure capacity; and
* an estimated supply timeframe based on each urban centre’s 10-year average dwelling take-up rate.

**Table 1 – Estimated dwellings in infill and Land Under Development**

| **Region** | **Estimated Dwellings, including Attached** | | **Estimated Years of Supply** |
| --- | --- | --- | --- |
| ***Land Under Development*** | ***Infill opportunities and vacant land*** |
| Greater Darwin | 4891 | 1820 | 11 years |
| Katherine | 66 | 117 | 8 years |
| Tennant Creek | 34 | 125 | 27 years |
| Alice Springs | 96 | 572 | 17 years |
| **Total** | **5087** | **2634** |  |

**Social and affordable housing**

*Update: In progress| First reported in March 2024 / Updated March 2025*

Across the NT’s 4 major centres (Greater Darwin, Alice Springs, Katherine and Tennant Creek) the   
NT Government has identified land holdings that will be utilised to deliver up to 100 new social housing dwellings under the Social Housing Accelerator Program.

The NT Government is currently planning for delivery of 102 social dwellings to be delivered under Housing Australia Future Fund (HAFF) Round 2 drawing on CEO (Housing) owned land.

Further opportunities to develop CEO (Housing) owned land, including refreshing aging stock through the Commonwealth’s national housing and homelessness reform agenda to increase supply is currently being investigated.

An estimated future potential allocation of social and affordable lots has been identified from   
Crown land greenfield developments. Estimated numbers are based on the Department of Lands, Planning and Environment policy targets for land for social, community and affordable housing within Crown land greenfield developments and are included in the below table for finalisation in March 2025.

**Table 2: Potential new social housing lots in the next 5 year**

|  | Potential lots within the next 5 years, | Potential lots within the next 5 years, |
| --- | --- | --- |
|  | 5% Social | 10% Affordable |
| **Land Under Development** | | |
| Greater Darwin | 38 | 116 |
| **Future supply-Current Commitment with full funding** | | |
| Greater Darwin | 15 | 30 |
| **Future Supply-Partially funded, future funding required** | | |
| Katherine | 7 | 15 |
| Tennant Creek | 3 | 5 |
| Alice Springs | 3 | 5 |
| **Grand Total** | **66** | **171** |

#### When undertaking redevelopment of existing social and affordable housing sites, the NT Government aims to deliver a minimum one-for-one return of dwellings wherever possible, based on the principle of no-net-reduction in social and affordable housing stock. Where possible, brownfield developments also aim to increase and/or optimise dwelling yield within the parameters allowed under the NT Planning Scheme.

#### Remote housing

*Update: In progress | First reported in March 2024 / Updated March 2025*

The delivery of housing through the remote community subdivision program aims to deliver 853 lots across 20 communities. As at 31 March 2025, 423 lots have been completed, 109 lots are under construction, and 339 lots are in the planning and design phase. There are 49 lots currently under construction that are forecast for completion within the 2024-25 financial year, subject to inclement weather.

Work is currently underway to determine future land release requirements to support up to an additional 2700 new remote public housing dwellings across 73 plus remote communities and selected town camps to be built over the next 10 years.

|  |
| --- |
| Measure 5 Planning Ministers will streamline approval pathways and prioritise planning control amendments to support diverse housing across a range of areas, including promoting medium and high-density housing in well-located areas close to existing public transport infrastructure connections, amenities and employment. |

## Zoning, planning and other amendments to support dense, well-located housing

Strategic Directions Planning Policy

*Update:* In progress/*First reported in September 2024 / Updated March 2025*

The NT Planning Commission has identified the need for an overarching Strategic Directions Planning Policy (SDPP) to provide direction on how the objectives of the *Planning Act 1999* are to be achieved; to ensure the planning framework responds to Territorians’ needs and aspirations; and to promote a prosperous, sustainable, liveable and resilient future.

In May 2024, the NT Planning Commission released a Discussion Paper to inform the development of the high-level SDPP. Consultation concluded on 31 August 2024. Submissions informed the development of the draft policy document, which will undergo further stages of consultation in quarter 2 of 2025.

Land Supply and Housing Diversity is a key theme being explored in the Discussion Paper. Specifically, the paper recognises that as the NT strives for population growth and seeks to reduce barriers to accessing secure housing, it is important that a diverse range of resilient housing options are available to cater for different incomes as well as cultural, workforce, household and stage-of-life needs, as well as personal aspirations and lifestyle choices.

Once complete the SDPP will set direction as to how future strategic land use plans can support this need.

#### Holtze development – new strategic land use plan *Update: In progress | First reported in March 2024 / Updated March 2025*

#### A new strategic land use plan (which is a new policy) for the Holtze residential development area (located centrally within the Greater Darwin Region), was approved in July 2024 for inclusion in the NT Planning Scheme. This is a planning policy that was completed by the NT Planning Commission in late 2023, and has been through a three stage public consultation process.

#### This land use plan has been developed based on the Compact Urban Growth Policy, which is included within the NT Planning Scheme and promotes high and medium density housing in a well located area, close to existing public transport, infrastructure connections, amenities and employment.

Greater Holtze will be the location of a large proportion of the new housing stock to be provided in the NT over the next 5 years. On 8 May 2024, the first land release for Greater Holtze was announced with the NT entering into a Development Agreement with a local company to deliver an entry level, urban residential subdivision of around 550 lots, in 18 stages over seven years. Lots within stages 1 and 2 of the development are now available for sale off-the-plan, with lot pricing starting from $189,000. Civil construction works commenced in May 2025 and first land titles are expected in September 2025.

The Holtze Land Release includes that the Developer must develop 5% of the total Developed Lots for Social Housing and return these lots to the Territory at nil cost. As part of the Holtze Land Release 28 Lots are planned be returned to the Territory for Social Housing.

**Social housing requirements for greenfield land**   
*Update: Ongoing | First reported in March 2024 / Updated March 2025*

The NT Government incorporates provisions akin to inclusionary zoning for affordable and social housing within many greenfield land releases in urban areas of the NT, through development agreements between the NT Government and private developers.

The NT Government is able to influence the proportion of new development that must be allocated for social and affordable housing.

In March 2025, the Australian Government announced funding of $25 million to boost housing in the NT through the Australian Government’s Housing Support Program Priority Works Stream. This funding includes $11 million to upgrade existing infrastructure networks (power, water and sewer) in Palmerston, which will support further development at Farrar West.

Government is negotiating with the Larrakia Development Corporation for delivery of a residential subdivision at Farrar West as part of the settlement of the Kenbi Land Claim, and to further support the release of residential land for future population growth. This development could provide up to 300 residential homes well located close to the Palmerston CBD, with provision for 5% of lots to be returned to the NT for Social Housing and 10% of lots to be allocated for Affordable Housing.

## Reforms to non-planning barriers preventing a diversity of housing

The lack of scale (i.e. population) in the NT strongly impacts the commercial viability of higher construction cost, large scale single buildings or integrated developments generally.

|  |
| --- |
| Measure 6 Planning Ministers will create accelerated development pathways and streamline approval processes for eligible development types, particularly in well-located areas, including to support the rapid delivery of social and affordable housing. |

## Identifying barriers in development approvals

### Key barriers to the timely issuing of development approvals

The simplicity of the NT planning system, including that the NT Planning Scheme applies across the Territory and in all local government areas, significantly reduces many potential barriers to the timely issuing of development approvals.

Key barriers that have a significant impact on the delivery of new social and affordable housing supply include negative (not-in-my-back-yard) community sentiment, seasonal weather patterns (delivery delays), constrained construction industry capacity and skilled labour shortages, and high construction costs relative to land and property values.

### Barriers to delivering housing where development approvals have been granted

#### Key barriers that have a significant impact on the delivery of new housing include seasonal weather patterns (delivery delays), constrained construction industry capacity and skilled labour shortages, and high construction costs relative to land and property values.

## Reforms to development approvals

### Reforms to social and affordable housing approval pathways

The NT Government recognises the need to ensure the ongoing supply of new land within greenfield urban Crown land releases to support the delivery of social, community and affordable housing in the NT. In August 2023, Government introduced the Land for Social, Community and Affordable Housing Policy which specifies the provision of a minimum of 5% social and community housing, and 10% affordable housing within commercially viable greenfield releases of Crown land. It is noted that the development of Crown land is the predominant means of land release in the NT, and this Policy therefore provides an effective means of implementing inclusionary zoning. The policy does not add to the cost of construction as the cost of setting aside land for social and affordable housing purposes is able to be achieved in a cost effective manner through Crown land Development Agreements with private developers.

Investigations are continuing on how the NT can deliver further initiatives for greater social and affordable housing approval pathways.

### Reforms addressing barriers to the timely issuing of development approvals

#### Planning approval process improvements - reduced red tape

*Enacted 31 July 2020 | First reported in March 2024*

On 31 July 2020, an amendment to the NT Planning Scheme took effect (associated with Government’s Planning Reform Initiative) which amongst other things, reduced regulatory burden and red tape associated with the planning approval process specifically for housing by:

* introducing streamlined tracks of assessment for all ‘housing’ development applications   
  (as well as a number of other types of developments). These applications now have the option of being assessed against only the basic ‘tick box’ planning requirements (such as height, setback, car parking etc.) and not whether or not they are appropriate in the location;
* removing the need for a planning application for fully compliant duplex developments; and
* creating a much more flexible outcomes based system which emphasises the importance of strategic ‘placed based’ planning. This includes identifying higher density infill development opportunities to streamline rezoning approvals.

The amendments provide expedited pathways for the delivery of housing, as well as for the achievement of increased housing densities in appropriate locations (above those normally allowed for within the existing zone).

### Planning reforms to address existing development approvals which have not been acted upon

The NT currently tracks all approved development applications for multi-storey unit complexes and reports on a monthly basis on land under development including tracking of all lots with approved subdivision/development permits (for detached dwellings and townhouses) throughout the NT. Compliant single detached houses, granny flats, and duplexes do not require planning consent in the NT.

### The Northern Territory’s position on planning and inclusionary zoning reforms to support permanent affordable, social and other specialist housing in developments[[2]](#footnote-3)

The NT Government incorporates provisions akin to inclusionary zoning for affordable and social housing within many greenfield land releases in urban areas of the NT, through development agreements between the NT Government and private developers. This is achieved in accordance with the Land for Social, Community and Affordable Housing Policy.

The NT supports planning measures to help deliver more affordable, social and other specialist housing in developments. Whilst the benefits of inclusionary zoning are recognised such as increased social inclusion and reduce the concentrations of disadvantage, care must be taken to ensure that it does not run counter to the broader goal of increasing the supply of new dwellings worsening overall affordability. Research needs to be undertaken to ensure such a reform does not add time, cost, complexity and uncertainty to the development approval process.

This is a policy area that would benefit from national leadership in establishing and facilitating regulatory coherence.

### Other reforms to development approval pathways

Relevant measures are already identified in Measure 3, noting that the NT Planning Scheme 2020 applies Territory-wide, and the NT Government has sole responsibility for the administration of planning in the NT. Therefore, there is no disconnect between local government and Territory level strategic and statutory planning policy.

## Initiatives to share planning data and improve visibility of factors affecting housing delivery

The NT is supportive of sharing any relevant data.

|  |
| --- |
| Measure 10 All levels of government will ensure the efficient use of government land, including the identification of surplus land suitable for housing and the delivery of best practice projects to support housing supply, diversity and affordability. |

## Well located government land suitable for housing

*Update: First reported in March 2024 / Updated March 2025*

The NT is unique in that the majority of its new greenfield developments are on vacant Crown land, particularly in the regional urban centres.

Table 3 outlines the anticipated dwellings expected from Crown land greenfield developments, categorised within the 4 stages of development and in accordance with the draft Land Development Strategy as follows:

1. Land Under Development (LUD): land that is in the hands of the developers, with reticulated infrastructure service connections to be provided through the subdivision development process to produce titled land to market. This land is identified in measure 4 whereas the Land Under Development below is solely Government owned land.
2. Land with Enabling infrastructure (LEI): is land that has design and construction of enabling infrastructure underway.
3. Land Under Investigations (LUI): Land that requires consideration of environmental, geotechnical works and land tenure.
4. Land Under Planning (LUP): is land that is undergoing or has underdone strategic integrated land use and infrastructure planning including subregional land use planning and area planning.

Projected years of supply is also included based on population projections from the NT’s Department of Treasury and Finance (and ABS data).

Table 3 identifies ample supply of government-owned land to support the next 20 years of growth and beyond.

**Table 3: Supply of Government owned land in the Northern Territory**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Land Under Development** | **Land with Enabling Infrastructure or Under Investigations / Land use Planning** | **Total estimated lot and dwelling supply across region** | **Years of supply\*** |
| ***Greater Darwin*** | | |  |  |
| Detached (lots) | 2,723 | 4700 | 7,423 |  |
| Attached (dwellings) | 606 | 440 | 1,046 |  |
| **Total Dwellings** | **3,329** | **5,140** | **8,469** | **14 years** |
| ***Katherine*** | | |  |  |
| Detached (lots) | 54 | 583 | 637 |  |
| Attached (dwellings) | 19 | 165 | 184 |  |
| **Total Dwellings** | **73** | **748** | **821** | **35 years** |
| ***Tennant Creek*** | | |  |  |
| Detached (lots) | 6 | 250 | 256 |  |
| Attached (dwellings) | 28 | 25 | 53 |  |
| **Total Dwellings** | **34** | **275** | **309** | **51 years** |
| ***Alice Springs*** | | |  |  |
| Detached (lots) | 66 | 637 | 703 |  |
| Attached (dwellings) | 30 | 63 | 93 |  |
| **Total Dwellings** | **96** | **700** | **796** | **20 years** |

*\* Based on average take up with population projections   
Note: the numbers are estimates and are subject to change.*

The NT Government has also identified land suitable for immediate development to support the delivery of up to 100 new dwellings under the Social Housing Accelerator (SHA). New supply to be constructed as part of the SHA, including expected distribution across different locations is outlined in the NT SHA Implementation Plan: <https://treasury.gov.au/sites/default/files/2023-11/shap-nt.pdf>

Another initiative is the NT Government’s Community Land Grant Scheme, which makes suitable Crown land available to eligible entities at a nil or reduced rent for the development of Community Infrastructure. This program has allowed developments by not for profit organisations on Zone CP (Community Purpose) land for housing types that provide 24/7 care. An example of land rented at nil cost under the Scheme includes for the development of 10 accommodation units by a community provider to support mental health rehabilitation.

Below is a best practice example of the development of Crown land in Katherine to achieve broader whole of government priorities. The concept plan identifies the delivery approach and vision for the

precinct which includes affordable and social housing, commercial land and community land for supporting services. Enabling district-level infrastructure such as key structuring streets and power, water and sewer headworks is delivered by the NT Government to facilitate future land releases through transparent market processes and to enable private sector land development.

Best practice examples of developing government land

|  |
| --- |
| Case Study – Katherine East Urban Village Precinct This development is a best practice example of the development of Crown land in Katherine to achieve broader whole of government priorities. The concept plan identifies the delivery approach and vision for the precinct which includes affordable and social housing, commercial land and community land for supporting services. Enabling district-level infrastructure such as key structuring streets and power, water and sewer headworks is delivered by the NT Government to facilitate future land releases through transparent market processes and to enable private sector land development. |
| **The Vision - Local shopping and urban opportunities**  A new neighbourhood centre is planned to support the existing and emerging Katherine East community as part of a Katherine East Urban Village Precinct.  **The Precinct**  Will incorporate a range of uses that are framed and focussed around a central park and linear open space link. The intent is to foster a range of urban living opportunities, including mixed use apartment living.    **Delivery approach and construction progress – enabling infrastructure, key roads and superlots**  Key structuring streets and enabling headworks infrastructure are being constructed. These works have been partially funded via a commonwealth agreement.  A range of lots and englobo lots will be made available to the market for development in sequence with the residential development front coming down from the north.  Key structuring streets and enabling headworks infrastructure are being masterplanned to enable a range of lots and englobo lots to be made available for future development and in sequence with the residential development front coming down from the north.  There is potential for the broader Katherine East area to deliver a further 600 dwellings, which accounts for approximately 40 years supply at current baseline take-up rates. It is anticipated that the provision of key strategic urban amenity elements will help foster the delivery of these dwellings in a greater variety of forms. |

1. For the purpose of this report it is assumed that development ready means land with infrastructure that is ready to sell and/or construct [↑](#footnote-ref-2)
2. Where appropriate and where such zoning and planning does not add to construction costs e.g., through the use of incentives such as density bonuses [↑](#footnote-ref-3)