# National Planning 
Reform Blueprint
Victoria September 2025 progress report

The Department of Transport and Planning proudly acknowledges Victoria’s Aboriginal communities and their ongoing strength in practicing the world’s oldest living cultures.

ISBN: 978-0-7311-9383-7

Authorised by the Victorian Government, Melbourne 1 Spring Street Melbourne Victoria 3000.

Telephone (03) 9655 6666.

© Copyright State of Victoria Department of Transport and Planning

Except for any logos, emblems, trademarks, artwork and photography in this document is made available under the terms of the Creative Commons Attribution 4.0 Australia licence.

Contents

Measure 2	1

How Victoria’s strategic plans will deliver on housing supply targets	1

Measure 3	2

Summary of planning, zoning, land release, density and other reforms	2

Measure 4	9

Key findings from a development ready land stocktake	9

Measure 5	10

Zoning, planning and other amendments to support dense, well-located housing	10

Reforms to non-planning barriers preventing a diversity of housing	13

Measure 6	15

Reforms to development approvals	15

Reforms to social and affordable housing approval pathways	15

Reforms addressing barriers to the timely issuing of development approvals	16

Planning reforms to address existing development approvals which have not been acted upon	17

Victoria’s position on planning and inclusionary zoning reforms to support permanent affordable, social and other specialist housing in developments	17

Other reforms to development approval pathways	18

Initiatives to share planning data and improve visibility of factors affecting housing delivery	20

Measure 10	21

Well located government land suitable for housing	21

Best practice examples of developing government land	21

# Measure 2 - Planning Ministers will report to National Cabinet on state, regional and local strategic plans before 1 March 2024 that reflect their jurisdiction’s share of housing supply targets agreed by National Cabinet and links with infrastructure pipelines.

## How Victoria’s strategic plans will deliver on housing supply targets

#### A new Plan for Victoria and local housing targets

On 20 September 2023, the Victorian Government announced the release of Victoria’s Housing Statement – The decade ahead 2024-2034 (the Housing Statement), which set a target to build 800,000 dwellings in Victoria over the next decade. This exceeds the National Cabinet housing target of 306,000 dwellings over five years, on a per capita distribution.

A key longer-term initiative included in the Housing Statement was to replace the current metropolitan planning strategy, Plan Melbourne, and regional growth plans, with a new plan for Victoria that will cover the whole state.

Plan for Victoria (PfV) was released by the Victorian Government on 28 February 2025 and is the state’s 30-year blueprint for how Victoria will grow over time and is structured around five pillars: housing for all Victorians, accessible jobs and services, great places, sustainable environments, and self-determination and caring for Country.

PfV aims to deliver an integrated land use and transport response that maximises the benefits of existing infrastructure and capitalises on the benefits of major new infrastructure investments such as the Metro Tunnel and the Suburban Rail Loop, which will take 600,000 cars off the road and open up new job and housing opportunities for Victorians whilst enhancing Melbourne’s productivity and liveability.

PfV sets out housing capacity targets for every Victorian local government area, specifying their share of the extra 2.24 million homes from the Housing Statement. In September 2025, PfV and housing targets were included in the Victoria Planning Provisions and all planning schemes (VC283).

PfV also acknowledges the role regional cities play in building more homes for all Victorians, and acknowledges the interconnected nature of Victoria’s cities, suburbs, towns, and regions in a coordinated response to building more homes and reaching the state’s full potential. As part of implementing PfV regional growth boundaries will be developed to manage outward sprawl of regional towns and settlements and encourage more homes in the centre of town.

In total, 22 actions are identified in PfV.  Key actions include:

- Implementing housing targets for every Victorian local government area

- Implementing new controls to streamline planning in activity centres

- Incentivising more social and affordable homes across the state

- Designing and building better quality homes and apartments

- Protecting tree canopies and introducing minimum open space requirements in planning

# Measure 3 - Planning Ministers will undertake planning, zoning, land release and other reforms, such as increasing density, to meet their jurisdiction’s share of housing supply targets agreed by National Cabinet.

## Summary of planning, zoning, land release, density and other reforms

Activity Centre Program (ACP)

Update: Progressing | First reported in March 2024

As part of Victoria’s Housing Statement, the Victorian Government is planning for more homes in activity centres across Melbourne so more Victorians can access homes in the places they want to live - closer to jobs, services, public transport and green, open space.

In 2024, work began on planning and consulting with the community on the first 10 pilot activity centres, estimated to deliver an additional 60,000 homes in and around the activity centres. Extensive consultation was undertaken on these activity centres and nearly 10,000 responses were received from the local communities, councils and stakeholders across two stages of consultation.

In February 2025, the Victorian Government finalised plans for the 10 pilot activity centres of Broadmeadows, Camberwell Junction, Chadstone, Epping, Frankston, Moorabbin, Niddrie (Keilor Road), North Essendon, Preston (High Street) and Ringwood.

The plans identify the best locations for more homes within each activity centre, and the most appropriate types of homes for each place. Along with associated planning scheme amendments, the plans propose new rules for building heights, setbacks, and other planning controls to allow more homes to be built there (Further details on the new planning controls for activity centres are reported under Measure 5).

The pilot program is being expanded to include another 50 train and tram zone centres where there is good access to public transport, jobs and services.

The locations of these centres have been chosen based on an analysis of transport capacity, market viability, access to jobs and services, and environmental considerations.

The expanded Train and Tram Zone Activity Centre Program will provide capacity for more than 300,000 additional homes by 2051, delivering more homes close to public transport.

The expanded program is being delivered with local communities, councils and stakeholders to better understand how these activity centres can improve access to housing while enhancing the things that make these centres great places to live.

Consultation is underway on the first 25 train and tram zone activity centres as part of the expansion’s first stage. Feedback is sought on draft maps depicting a ‘core’ where taller apartment buildings would be allowed, and a ‘catchment’ area where gentler building heights, low-rise apartments and townhouses could be developed. Consultation on the remaining train and tram zone activity centres, as part of a second stage, will commence in October 2025.

Making it easier to build a small second home

Update: Enacted | First reported in March 2024

On 14 December 2023, as part of delivering Victoria’s Housing Statement, Victoria’s planning and building systems were amended to make it easier to build a small second home.

The reforms facilitate the delivery of housing in Victoria by making a small second dwelling with a gross floor area of 60 square metres or less, exempt from requiring a planning permit in most residential and rural zones if specified requirements are met.

Analysis by the Department of Transport and Planning found there are around 700,000 lots of 300 square metres or larger eligible to have a small second home in residential zones across the state, and roughly 2,450 in rural zones – all of which have no overlays.

Research undertaken by the University of Sydney indicates this type of approach has increased the supply of secondary dwellings representing approximately 5,000 dwellings or 10 per cent of all dwelling approvals per annum.

Amendment VC253 made changes to the Victoria Planning Provisions and all planning schemes, and the Building Amendment (Small Second Dwellings) Regulations 2023 made changes to the Building Regulations 2018 to coordinate the approval processes to build a small second home.

Making it easier to subdivide blocks and build new homes

Update: Enacted |First reported in March 2025

In October 2024 the Victorian Government announced that it would examine how the planning and building systems can be streamlined to enable more Victorians to add a second home, build two new homes, or subdivide a block into two lots.

In response to that review, the Victorian Government has expanded the streamlined 10-business day VicSmart assessment process to apply to building two dwellings on a lot and for the subdivision of residential zoned land into two lots.  The new fast-tracked process was implemented on 18 September 2025 by Amendment VC288.

Key criteria must be met to achieve the fast approval, such as siting, privacy and design standards. In addition, important protections like heritage and environmental overlays still apply, so new homes fit well into existing neighbourhoods.

The new streamlined process is estimated to save applicants on average more than $2,400 in fees, cut around two months off assessment time, and provide a more certain planning process.

The new rules will boost housing supply where people want to live – in the suburbs close to transport, schools, services and jobs. The move follows the government's change to regulations introduced in 2023, allowing homeowners to build small second homes, such as granny flats, without a planning permit.

Priority Precincts

Update: Progressed | First reported in March 2024

Priority precincts are areas identified in Plan for Victoria where transformational change is being planned to deliver new jobs and homes. They are Arden, Docklands, Fishermans Bend, Footscray, East Werribee, Parkville, Sunshine, Richmond to Flinders Street, La Trobe and the first six Suburban Rail Loop (SRL) precincts (Box Hill, Burwood, Glen Waverley, Monash, Clayton, Cheltenham).

Priority precincts are key places to build more homes, improve housing affordability and choice, create jobs and support industry. This is important to ensure Victoria’s long-term success and prosperity.

Priority Precincts capitalise on the benefits of major infrastructure investments like the Suburban Rail Loop, Metro Tunnel and the Melbourne Airport Rail Stage 1.

Priority Precincts are expected to deliver around 150,000 homes with opportunity for more homes to be built as Priority Precincts grow over time. Recent activity is outlined below.

On 25 February 2025 Amendment VC257 introduced a new Built Form Overlay (BFO) and on 28 February 2025, Amendment VC274 introduced a new Precinct Zone (PRZ) into the Victoria Planning Provisions. The BFO is a streamlined Overlay facilitating higher density development and the PRZ is a special purpose zone that provides a framework for the implementation of strategic work (such as structure plans and implementation plans) in priority precincts.

When applied to land, the PRZ and BFO and accompanying schedules will:

- facilitate substantial change in use and development in line with the defined role of that precinct; and

- support a streamlined assessment process for applications that will contribute to addressing Victoria’s current and urgent housing supply, housing affordability needs, and stimulate economic growth.

The new PRZ has not been applied to any land at this time, however, it is proposed to be used to help facilitate the development of 70,000 new homes across the six Suburban Rail Loop (SRL) East Precincts. Progress on planning for the first six SRL East Precincts is reported separately under Measure 3 ‘Suburban Rail Loop (SRL)’.

The PRZ (and the BFO) will become the preferred zoning and built form control tools for state significant priority precincts going forward, including application in Sunshines’s Albion Quarter and in the Fishermans Bend Employment and Innovation Area.

In May 2024 an Opportunity Statement was released for the East Werribee Precinct outlining the Victorian Government’s vision for East Werribee as a new centre for jobs and housing in Melbourne’s growing western corridor. In September 2025, it was announced that Development Victoria will act as master developer for the East Werribee Precinct. Development Victoria, the State’s development agency, will work closely with key stakeholders and the community to coordinate the planning and delivery of the precinct and will partner with the private sector to support the delivery of new housing and employment opportunities. Early development opportunities, including housing and jobs, have been identified and early work on land release for these opportunities is underway.

DTP is partnering with Victorian School Building Authority (VSBA) and Development Victoria (DV) to build a new P-9 school with 1,250 places and a specialist school with 168 places in Point Cook. Both schools will be open for term 1 in 2026 and a kindergarten will open on the same site in 2027. The precinct will also benefit from major planned investments, including the future Bay West Port, a new Intermodal Freight Terminal and significant transport network upgrades.

DTP has commenced work on a Structure Plan which will support the transition of Albion Quarter from the current mix of industrial-focused businesses to supporting Melbourne’s next generation of jobs, innovation and services, and provide a space for new residential dwellings close to public transport and active transport connections.

The Fishermans Bend Integrated Transport Plan was released in September 2025 and identifies a suite of integrated transport initiatives over three broad delivery horizons to support the realisation of the vision and sustainability goals for Fishermans Bend. The plan provides a refined route for a future rail tunnel through Fishermans Bend and Docklands with two stations in Fishermans Bend (Innovation and Sandridge Precincts). The refined route will be future proofed through planning protections.

The Department of Transport and Planning continues to deliver Stage 1 of the Fishermans Bend Innovation Precinct (with Development Victoria), with completion expected by mid-2026.

The Government has undertaken consultation on the Urban Renewal Area Development Contributions Plan (DCP) and Montague Precinct Implementation Plan (MPIP) to guide the growth and change of the current development front in Fishermans Bend over the next decade. A public Advisory Committee process took place in late 2024 to provide independent review and advice on the proposed DCP. The Advisory Committee report was provided in April 2025 and the government is currently considering the recommendations. When finalised, the DCP will provide certainty on the funding and delivery of essential infrastructure for urban renewal in Fishermans Bend.

Suburban Rail Loop (SRL)

Update: Progressed | First reported in March 2024

Suburban Rail Loop (SRL) is an integrated transport and place-making project, designed to help address the challenges of Melbourne’s continuing population growth and increase housing supply.

It is a 90km orbital rail loop that will link every major railway line from the Frankston line in Melbourne’s south-east to the Werribee line in the west.

By adding a wheel to the city’s ‘hub and spoke’ rail network, with convenient passenger interchanges at existing stations, it will slash travel times, ease pressure on public transport and cut road congestion.

In addition, the new SRL stations will become anchor points for precinct activity and investment, helping to shape Melbourne’s unprecedented growth, connecting people to jobs and services closer to where they live, and delivering more affordable and quality housing choices in Melbourne’s middle suburbs.

As part of SRL East (Cheltenham to Box Hill), Planning Areas have been declared around the six SRL East stations and the Suburban Rail Loop Authority (SRLA) is undertaking structure planning to consider how the benefits of the new rail infrastructure can be optimised by increasing more affordable housing options in these established areas.

The Planning and Environment Act 1987 and Suburban Rail Loop Act 2021 enable the SRLA to function as a planning authority in declared areas around the SRL East stations, alongside councils. This legislation enables SRLA to undertake structure planning, in consultation with the community, local government and other key stakeholders, to consider land use and requirements for services and amenity outcomes such as open space.

SRL will support Plan for Victoria by creating a city of centres, with investment, new housing to reduce the reliance on a central business centre and to reshape how Melbourne grows in the decades ahead.

SRLA has been capturing community and stakeholder feedback since 2019 and is continuing to consult with residents, businesses and stakeholders on both the rail infrastructure works as well as its structure planning program for the future of the areas around the new SRL stations. The need for greater housing choice and affordable options in established suburbs underpins the structure planning process.

In August 2023 an SRL Precincts Discussion Paper was released to report on feedback to date and this was followed by the release in early December 2023 of six Draft SRL Precinct Visions – supported by an awareness campaign to encourage people to get involved and provide their feedback on how SRL East Precincts around the new stations should evolve. The project has now entered its next phase, with the release of draft structure plans and draft planning scheme amendments showing how neighbourhoods around the six SRL stations can grow.

Community consultation was undertaken during March and April 2025. An advisory committee was appointed on 1 June 2025 and commenced a public hearings process in late August 2025. Following the independent advice of the advisory committee, planning scheme amendments will be finalised in 2026.

Unlock surplus government land

Update: Progressed | First reported in March 2024

Victoria’s Housing Statement includes a commitment to unlock and rezone surplus government land to deliver around 9,000 homes across 45 sites in metropolitan Melbourne and regional Victoria. As part of this work, a target has been set of at least 10 per cent of affordable homes to be built across these sites.

The Small Sites Pilot, launched in July 2024, with four sites across inner Melbourne. An Expression of Interest (EOI) was issued in August 2024, followed by a Request for Proposal (RFP) in October 2024, inviting proposals from successful EOI respondents.

A further 10 sites from across Melbourne, Bendigo and Geelong, will be released through an EOI in October 2025 as part of the Small Sites Program.

It is anticipated that the 14 sites will deliver up to 1,000 new homes including 10 per cent affordable housing.  Development Victoria is managing the market process to select developers for these sites.

Two additional government land sites near Oakleigh and Footscray stations – along the Metro Tunnel’s train line – were released to market in November 2024 as part of a separate procurement process. VicTrack is overseeing the EOI and Request for Proposal (RFP) process for these two sites on behalf of the Victorian Government. The process will explore commercial partnerships that will boost the number of homes on these surplus sites, which are well suited for mid-rise living and have the potential to deliver around 240 homes with a minimum of 10 per cent affordable homes.

In October 2024, the Victorian Government rezoned a surplus government land site located at Denmark Street, Kew (formerly home to VicRoads’ offices). The rezoning from Transport Zone to a mix of Commercial and General Residential zones allows for the future redevelopment of the site, unlocking the potential for approximately 500 homes to help meet the area's growing housing demand. The site is located close to Kew Junction, which is one of the 50 new ‘train and tram zone’ Activity Centres identified for more housing growth. In March - April 2025, Development Victoria undertook community consultation to help shape the future of the site. A tender process for private sector development partners is currently underway, with successful partners to be announced in 2026.

Development Victoria are currently exploring development options, including the potential adaptive re-use of the southern building. They are also investigating partnerships with the private sector to help deliver aspects of the development, ensuring a diverse mix of housing options across the site with community engagement having occurred in March and April 2025.

Development Victoria and the Department of Transport of Planning are delivering the urban renewal of the Victorian Government's landholding in the Arden Precinct, which is approximately 12 hectares of land located around the new Arden Metro Station. A competitive market process is underway to identify a Master Developer for Arden Central. This is reported separately under Measure 3 (below) – See ‘Activate the Arden Precinct’.

Activate the Arden Precinct

Update: Progressed | First reported in March 2024

The Arden Precinct presents a landmark urban renewal opportunity in an accessible and vibrant part of central Melbourne. The precinct aims to home 20,000 people by 2051.

Due to open in late 2025, the streets surrounding Arden Station are designed for walkability and pedestrian safety, with wide footpaths and a signalised crossing on Laurens Street to the station entrance. Outside the station there are more than 120 bike parking spaces, along with separated bike lanes to make cycling safer and easier.

Development Victoria is leading a multi-stage market search process to select a development partner for the government owned land in the Arden Precinct, known as Arden Central which is approximately 12 hectares of land located around the new Arden Metro station.

A competitive market process is underway to identify a Master Developer for Arden Central. Development proposals are now being assessed.

A 10-year plan for Melbourne's greenfields

Update: Progressing | First reported in March 2025

In October 2024 the Victorian Government released its 10-year plan for Melbourne's greenfields – a decade-long plan to deliver 27 new greenfield areas across Melbourne’s outer south-east, north, and west. The 10-year plan will provide a framework for industry to unlock 180,000 homes.

The plan represents a pipeline of new land in greenfield areas and reinforces the Victorian Government’s commitment to achieving its target of 30 per cent of new housing growth in greenfield areas.

The Victorian Government is planning for future housing in the newest suburbs with 27 new Precinct Structure Plans (PSPs) that will be better sequenced and coordinated with infrastructure delivery. This means 22 PSPs will be completed by 2034-35, and the remaining PSPs will be under preparation.

Through the unlocking program, the Victorian Government will also work with councils and industry to unlock constrained zoned land, identifying and addressing issues preventing high yield zoned land from being developed.

Government will also review existing PSPs that are not yet fully developed to understand opportunities for increasing the number and types of homes where there is sufficient planned infrastructure (transport, schools and community facilities) to support them.

Staging provisions will be included in future PSPs as required to ensure infrastructure delivery keeps pace with development and land can be adequately serviced when it is released.  Government will regularly review the future pipeline of greenfield land supply to make sure it is delivering housing choice in the right areas.

On 1 January 2025, the Victorian Planning Authority (VPA) was integrated into the Department of Transport and Planning. This will ensure that strategic, transport, statutory and spatial planning are integrated to cut delays and duplication and deliver faster and better structure planning.

The Victorian Government is unlocking more capacity for new homes and jobs on regional greenfield sites in Shepparton South East, Bannockburn South East, East of Aberline, Ballarat North and Merrimu.

# Measure 4 - Planning Ministers will identify well-located ‘development ready’ land before 1 March 2024, having appropriate regard to the protection of land with key attributes e.g. environmental or economic.

## Key findings from a development ready land stocktake

The Victorian Government undertakes a regular stocktake of development ready land via the Urban Development Program (UDP). The UDP tracks the pipeline of residential development across metropolitan and regional greenfields and redevelopment sites. By focusing on key sections of the development pipeline the stock of development ready land can been identified. Development ready land is land with infrastructure that is ready to sell and/or construct.

In the Metropolitan Greenfields pipeline, the UDP reports quarterly on lots with a title and proposed lots:

Lots with a title represents land that has been subdivided and titled in the relevant/previous calendar year. It has services connected and is ready for dwellings to be built.

Proposed lots are lots that are part of a proposed subdivision plan but have not yet been titled.

In the Metropolitan Major Redevelopment sites pipeline the UDP reports annually on sites where there is a firm expectation sites will progress to development in the near future:

Projects that have been approved and/or taking sales enquires and registrations.

In the Regional development pipeline the UDP reports annually on greenfield land supply in the major urban centres, providing the same short-term development information as the metropolitan equivalent:

Lots with a title represents land that has been subdivided and titled in the relevant/previous calendar year. It has services connected and is ready for dwellings to be built.

Proposed lots are lots that are part of a proposed subdivision plan but have not yet been titled.

Relevant UDP data has been reported on as part of the Blueprint metrics framework.

# Measure 5 - Planning Ministers will streamline approval pathways and prioritise planning control amendments to support diverse housing across a range of areas, including promoting medium and high-density housing in well-located areas close to existing public transport infrastructure connections, amenities and employment.

## Zoning, planning and other amendments to support dense, well-located housing

Future Homes program

Update: Progressed | First reported in March 2024

On 22 September 2023 the Victoria Planning Provisions were updated, as part of delivering Victoria’s Housing Statement, to expand the Future Homes program from a single pilot location in the City of Maribyrnong, to state-wide implementation across all metropolitan and regional councils.

Future Homes provides four sets of readymade architectural designs for 3-storey apartment developments which can be purchased by developers and adapted to a site through a streamlined planning process.

The development must be located in either the General Residential Zone or Housing Choice and Transport Zone, and within 800 metres of an activity centre or passenger railway station.

Future Homes exemplar designs incentivise developers to build better homes for occupants, better developments for neighbours, and better performing buildings for the environment.

The reforms provide support to the development sector through ready-to-use plans and streamlined planning processes, designed to create planning certainty and halve typical planning timeframes.

Amendment VC243 was gazetted on 22 September 2023. It expanded the Future Homes program across Victoria through the insertion of a new clause in the Victoria Planning Provisions – clause 53.24 (Future Homes).  To date, 22 sets of plans have been sold and there have been three Future Homes applications supported by the Department of Transport and Planning, one in regional Victoria and two in metropolitan Melbourne. Two projects have recently commenced construction and combined, will deliver 31 new high-quality homes.

Great Design Fast Track pathway

Update: Progressed | First reported in March 2025

In October 2024, the Victorian Government announced it would introduce a new fast-tracked pathway to promote, reward and expedite the construction of high quality, sustainable and innovative townhouses and apartment buildings.

In April 2025, Amendment VC280 introduced Clause 53.25 ‘Great Design Fast Track’ (GDFT) into the Victoria Planning Provisions and all planning schemes. This is an accelerated pathway to facilitate the delivery of residential developments of two to eight storeys in height comprising eight or more homes that demonstrate specified principles for great design. It applies statewide and operates similarly to the existing DFP (reported under measure 6), with the Minister for Planning the ultimate decision-maker on applications. Like the current DFP, applications are subject to the same level of assessment and opportunity for consultation as per the standard assessment process. Decisions made under the GDFT cannot be appealed by third parties, such as neighbours, at the Victorian Civil and Administrative Tribunal (VCAT). This increases certainty for applicants, reduces cost, and gets homes built more quickly.

The GDFT will encourage developers to create high-quality, innovative, and sustainable projects that enhance the visual appeal and long-term value of neighbourhoods. The pathway is supported by seven design principles to ensure high standards of design, sustainability, and liveability in the final builds. The Office of the Victorian Government Architect leads the assessment of applications against the design principles, ensuring a high standard is upheld.

The new state design book complements the new pathway by showcasing pre-existing examples of well-designed developments that demonstrate the Pathway’s guiding design principles. The state design book will provide confidence to both developers and communities about the kinds of high-quality townhouses and apartments they can expect to see delivered through the GDFT.

State Design Book

Update: Progressed | First reported in March 2025

In October 2024, the Victorian Government announced the new state design book with examples of high-quality developments that are already built, and best practice principles for well-designed apartments and townhouses. The state design book will provide confidence to both developers and communities about the kind of high-quality townhouses and apartments they can expect to see delivered.

The first part of the State Design Book has been released and contains the GDFT Design Principles and gives guidance on how they can be interpreted. The next part of the book will include built examples of townhouses (two to three storeys), low-rise apartments (up to five storeys) and mid-rise apartments (up to eight storeys), that showcases what living in an apartment or townhouse can look like. To create the next part of the book, community nominations were sought between April – June 2025. Once finalised, a selection of nominated buildings will be published in part two of the state design book.

The Victorian Government will also help to get these well-designed buildings off the ground by securing government-owned land for innovative ‘demonstration’ developments.

The developments will have to demonstrate high quality design, liveability and sustainability, including modern methods of construction – and be made open to the Victorian public to experience.

These demonstration buildings will then be made available to become homes for Victorians to buy or rent.

Clearer planning controls for Activity Centres and surrounding catchments

Update: Enacted | First reported in March 2024

As part of delivering the Activity Centre Program (reported under Measure 3), two new planning controls have been created to support the faster delivery of more homes in and around activity centres. They include:

- A new Built Form Overlay (BFO) and accompanying local schedules will set out specific design and built form requirements to facilitate the preferred scale of development in identified activity centres and priority precincts.

- A new Housing Choice and Transport Zone (HCTZ) will facilitate a diversity of housing at increased densities in locations around identified activity centres and other well-serviced locations with convenient access to jobs, public transport and services.

These new tools have been developed specifically to support housing growth in and around activity centres and other well-serviced locations in line with Victoria’s Housing Statement. In general terms, the vision is for taller buildings in the immediate 'core' of the activity centre where the train station and built-up commercial centre is located, and gentler, scaled height limits and more low-rise apartments in the walkable 'catchments' up to 800 metres surrounding the core.

These planning tools are also available for councils and other planning authorities to use. The creation of these new planning tools will make it easier for councils and planning authorities to encourage more homes to be built close to public transport, jobs and services in their own municipalities, helping all levels of government to play their part in delivering more homes for Victorians.

Legislative reforms to strengthen Victoria’s planning system

Update: Progressed | First reported in March 2024

Victoria’s Housing Statement committed to implementing priority legislative reforms that include implementing Red Tape Commissioner recommendations in the shorter-term and undertaking a full review and rewrite of the Planning and Environment Act 1987 in the longer-term. Proposed legislative reforms will build a modern, fit-for-purpose planning system, establish and clarify timeframes for decisions, as well as looking at the roles and responsibilities of everyone involved in Victoria’s planning system – including councils, the Minister for Planning, the Victorian Planning Authority and the Department of Transport and Planning.

The initiative will help achieve faster approvals of housing and rezoning of land for residential development, reducing associated time and costs to enable Victoria to grow and prosper in a sustainable way.

The Consumer and Planning Legislation Amendment (Housing Statement Reform) Bill 2024 was passed by the Victorian Parliament and received Royal Assent on 18 March 2025. It will implement Red Tape Commissioner recommendations to improve planning permit and amendment processes as well as streamline planning panel processes and proceedings before the Victorian Civil and Administrative Tribunal. The benefits of these reforms are likely to be minor for each relevant application, but when multiplied over the large number of permit applications and other activities the amendments relate to, they are expected to deliver significant benefits.

Work is also underway on the review and rewrite of the Planning and Environment Act 1987. An initial round of targeted consultation has been undertaken to assist in identifying priority areas for reform, including in relation to areas identified in the National Planning Reform Blueprint. Further targeted consultation was undertaken in early 2025.

Significant reforms are being developed as part of the review and rewrite of the Planning and Environment Act 1987 to ensure it provides a modern, fit for purpose planning system.

As part of the rewrite, the Victorian Government has confirmed it will look at:

- The time and costs associated with structure plans and rezoning, with possible legislative change to replace the current one-size-fits-all planning scheme amendment process.

- Further reducing planning permit delays and blockages, including different assessment and approval processes for projects that have a lesser impact.

Unlocking Strategic Sites Pathway

New Program: Announced September 2025

In September 2025, the Victorian Government announced it will expand the Development Facilitation Program to include a new Unlocking Strategic Sites pathway. The new pathway focuses on opportunities to unlock housing and employment opportunities on large, underutilised sites, including industrial or institutional sites, golf courses, racing tracks, and surplus government land.

Eligibility Requirements:

- Sites must be minimum 2 hectares in size

- Sites must be located within township or urban growth boundaries

- Proposed use and development must align with strategic policy objectives

- Residential projects must include 10% affordable housing

Councils and developers have been invited to submit Expressions of Interest (EOIs) by 17 November 2025.

## Reforms to non-planning barriers preventing a diversity of housing

Commercial to Residential

Update: Completed | First reported in March 2024

The Victorian Government has completed its work on this Housing Statement initiative, working with industry to explore the barriers to the conversion of commercial buildings and successfully piloting a planning assessment and approval pathway.

The program successfully demonstrated the utility of assessing adaptive reuse proposals through the expedited Development Facilitation Program pathway. However, it also highlighted that financial feasibility remains the core challenge in delivering adaptive reuse developments.

The Property Council of Australia has advised that it will continue to work with industry partners to better understand and quantify the incentive settings required to encourage more adaptive reuse developments.

The Department of Transport and Planning will further embed adaptive reuse into its BAU work by supporting negotiations between proponents and key stakeholders on incentives and supporting the measurement of emissions generated through the construction process as part of its assessments. The Victorian Government will also continue investigating adaptive reuse opportunities as part of plans to deliver around 9000 new homes on surplus government land.

New Infrastructure Contribution System

Update: Progressed | First reported in March 2025

In October 2024, the Victoria Government announced its intention to create a better, fairer system for property developers to contribute to funding for local infrastructure and services in the areas where they build more homes.

Under the plan, funding will be invested back into communities where more homes are built for the things they need, including:

- roads, paths and public transport

- new and upgraded schools

- upgraded health and community facilities

- parks, playgrounds, sport and recreation spaces, and more.

The Victorian Government is working with key members of its industry Working Group to develop the new statewide developer contributions model. The group provided advice to government in April 2025, noting the importance of a reformed system to support communities where more homes are being targeted around transport, services and jobs, such as in inner and middle ring municipalities of Melbourne. The government is currently considering the Working Group’s advice.

While this long-term statewide reform is being designed and implemented, the Victorian Government is introducing a new pilot developer contribution system in the first 10 Pilot Activity Centres across Melbourne (reported under Measure 3), where more homes will be delivered near transport, jobs and services.

Developers building new homes in the Pilot Activity Centres will be required to make a contribution from 1 January 2027. Contributions will go towards new and upgraded infrastructure including public transport, roads, upgrades to parks and community facilities.

# Measure 6 - Planning Ministers will create accelerated development pathways and streamline approval processes for eligible development types, particularly in well-located areas, including to support the rapid delivery of social and affordable housing.

## Reforms to development approvals

### Reforms to social and affordable housing approval pathways

Facilitating residential development with affordable housing

At the release of the Housing Statement on 22 September 2023, the Minister for Planning (the Minister) introduced a new state-led fast-track planning application pathway for Significant Residential Development with Affordable Housing at Clause 53.23 of the Victoria Planning Provisions (VPPs). To be eligible for this streamlined planning pathway, all residential development must include at least 10 per cent of the total number of dwellings to be affordable housing. This will encourage a significant proportion of new development to provide accommodation that is affordable for households on very low to moderate incomes.

The Development Facilitation Program (DFP) within the Department of Transport and Planning (DTP) was given the responsibility to facilitate and administer the new pathway. The DFP was initially established in 2020 to facilitate economically significant, employment generating development projects.

The new pathways added to the existing powers and responsibilities of the Minister for Planning in relation to residential development, including:

- The responsibility for significant residential planning applications (meeting minimum eligibility criteria) within the City of Melbourne, Central Geelong and Central Dandenong (amongst other geographical areas)

- Ministerial powers (under the Planning and Environment Act 1987) to “call-in” planning applications from local government and VCAT, and to amend Victorian Planning Schemes to facilitate development projects, and

- The power to “exempt” government funded housing development projects from the requirements of the planning scheme under Clause 52.20 of the VPPs (initially introduced to support the delivery of the Government’s Big Housing Build initiative).

Subsequently, the Minister has introduced ‘Great Design Fast Track’ and the ‘Unlocking Strategic Sites’ pathways, which are reported under Measure 5.

Overall, the pre-existing and introduced state-led application pathways have been successful in delivering big decisions faster, facilitating the approval of thousands of new dwellings and residential lots.

### Reforms addressing barriers to the timely issuing of development approvals

Speeding up approvals

Update: Progressed | First reported in March 2024 under the heading ‘Clear the backlog’

Victoria’s Housing Statement announced on 20 September 2023, includes an initiative to establish a new dedicated case management team to clear the backlog of 1,400 housing permit applications which at that time had been lodged with councils for more than six months without a decision.

The case management team worked with project proponents, local councils, and referral agencies to resolve issues delaying council decision-making – to avoid projects ending up in the Victorian Civil and Administrative Tribunal (VCAT) and to get homes built.

Over 85 per cent of planning permit applications for townhouses or apartments on the initial backlog list that had been pending a decision for more than six months have now been processed. For applications with a development cost exceeding $10 million, all but seven have been finalised, the remaining applications are either on hold or cannot be determined due to outstanding proponent matters. In total, these approved developments account for approximately 8,900 new dwellings, substantially clearing the initial backlog.

The case management team is currently monitoring and actively working with stakeholders to speed up approvals associated with permit applications which have a development cost greater than $10 million and have been in the planning assessment process for more than six months.

Rural and Regional Planning Cadet Program

Update: Progressed | First reported in March 2025

The Rural and Regional Planning Cadet Program (Cadet program) is a jointly funded initiative by the Commonwealth and Victorian Governments. The aim of the Cadet program is to support new planners to enter the rural and regional local government workforce. This program will directly address a state shortage of planners that is slowing planning processes – and slowing down approval of new homes.

The Cadet program will provide funding to rural and regional councils to subsidise the accredited tertiary institution tuition fees of a planning cadet they employ. This will help build land use planning capability and capacity across the 48 rural and regional councils, ensuring councils are sufficiently resourced to meet their statutory and strategic planning obligations and support the delivery of the local government housing targets specified in PfV.

Currently, the Cadet program is supporting the tertiary studies of 16 cadets across 11 councils. A second expression of interest process with local councils has now commenced.

The Victorian Government’s Regional Planning Hub program further supports rural and regional councils plan and develop their municipalities and shires by providing statutory and strategic planning support and resources that can:

- assist councils with peak workloads and priority developments

- build land use planning capacity and capability within councils

- improve planning schemes to simplify processes and approvals

- help with significant regional planning projects.

### Planning reforms to address existing development approvals which have not been acted upon

Acting on and delivering approved housing under the planning system relies on the private sector as the main provider and they may withhold progressing development if they consider a project unviable. This may be due to a range of reasons such as increased building costs, rising interest rates or difficulty securing labour. Anecdotal evidence has identified land banking practices among developers as a key barrier. This occurs when developers hold onto vacant land or permit-approved developments to await more ideal market conditions.

To discourage long-term land banking and encourage new housing developments, from 1 January 2026, Victoria’s Vacant Residential Land Tax will be expanded to include undeveloped residential land in metropolitan Melbourne that has not been developed for five years.

### Victoria’s position on planning and inclusionary zoning reforms to support permanent affordable, social and other specialist housing in developments

Social and affordable housing outcomes are secured through negotiated agreements under the Planning and Environment Act 1987. These can require the provision of affordable housing as part of private developments and are negotiated with private landowners during the planning approvals process. To support the negotiation of affordable housing outcomes planning incentives can be provided through a variety of tools, including uplift (such as density bonuses), value capture (based on an agreement to provide affordable housing when the land was rezoned), and precinct or area targets set by local government to signal to landowners the council’s objectives to secure affordable housing. Additionally, reforms made to the Victoria Planning Provisions now ensure that all residential development applications that opt into the streamlined DFP approvals pathways, must provide at least 10 per cent of total dwellings to be affordable housing or an equivalent measure to the satisfaction of the Minister for Planning.  On the 45 sites of surplus government land that are set to be unlocked, as announced in the Housing Statement, a target of 10 per cent affordable housing has also been set.

The Victorian Government is focussing on immediate social and affordable housing outcomes that can be secured using tools within the existing planning framework. This includes a commitment to explore the development and consideration of locally specific targets for social and affordable housing, which was an action identified in Plan for Victoria, the state’s planning strategy. In addition, the new Built Form Overlay (BFO) and Precinct Zone (PRZ) introduced in February 2025 allows for a public benefit uplift framework to be implemented that can include a requirement for the provision of affordable housing.

### Other reforms to development approval pathways

Deemed to comply residential development standards – ‘Townhouse and Low-Rise Code’ and ‘4 Storey Apartment Standards’

Update: Enacted | First reported in March 2024

Victoria’s Housing Statement includes an initiative to streamline planning permits for housing by establishing ‘deemed to comply’ standards that will speed up decisions.

In February 2025, the Victorian Government announced the introduction of two new sets of planning rules, the ‘Townhouse and Low-Rise Code’ (the Code) and the ‘4 Storey Apartment Standards’.

The new Code and standards build on the 14 ‘deemed to comply’ standards introduced in late 2023 and finalise the codification of these standards into Victoria’s planning system.

The new Code will implement new rules, called ‘deemed to comply’ standards, for assessing multi-residential developments of three storeys or less. If a planning application is ‘deemed to comply’ with these standards, it will benefit from a faster and more certain permit process.

The new rules set basic but important standards for good development, like setbacks, tree coverage, bedroom size, sunlight, overshadowing and overlooking.

The changes mean that council planners can quickly approve permits for townhouses and apartment buildings up to three storeys, so long as they meet the new standards and they‘ll only assess aspects of a permit that don’t comply with those standards.

The new assessment pathway will boost housing supply and affordability by making assessment processes efficient and straightforward, with an anticipated reduction in residential planning permit approval timeframes by up to 3 months.

The reform will provide more certainty for developers and clear community expectations.

The new Code and standards were gazetted on 6 March 2025 (Amendment VC267) and commenced operation on 31 March 2025.

The Single Home Code

New: Enacted | September 2025

The Single Home Code was implemented by Amendment VC282 on 8 September 2025 to streamline approvals for single homes and small second dwellings on lots under 300 square metres.

Under the code, if applicable standards are met, the application is ‘deemed to comply’, meaning no further assessment is required and the application cannot be refused based on that requirement. Also, if a development meets all applicable standards there are no third-party appeal rights to the Victorian Civil and Administrative Appeal Tribunal.

The existing fast tracked 10-day VicSmart permit process for single dwellings and small second dwellings has also been updated to work with the new requirements.

The new Single Home Code will:

- facilitate quicker and more efficient decision making

- provide greater transparency and certainty for applicants, decision makers and the community about what is acceptable development and how it is assessed

- ensure residential development is sustainable and provides reasonable standards of amenity for existing and new residents.

Reduce the need for planning permits for single dwellings

Update: Enacted | First reported in March 2024

As part of delivering Victoria’s Housing Statement, Amendment VC243 amended the Victoria Planning Provisions and all planning schemes to:

Remove the need for a planning permit for a single dwelling on a lot of 300 square metres or more.

Allow single dwellings on lots less than 300 square metres to qualify for the VicSmart permit process – meaning permit applications will be decided in 10-days.

The reforms will reduce the number of single dwelling residential developments that need a planning permit, and speed up decision-making for single dwellings where a permit is required.

The reforms will result in fewer planning permits in the system and reduced administrative burden.

Developers and families seeking to build a new home or extend an existing home will benefit from more timely and efficient planning outcomes.

Making it easier to build a small second home

Update: Enacted | First reported in March 2024

Reported as part of Measure 3.

On 14 December 2023, as part of delivering Victoria’s Housing Statement, Victoria’s planning and building systems were amended to make it easier to build a small second home.

Amendment VC253 made changes to the Victoria Planning Provisions and all planning schemes, and the Building Amendment (Small Second Dwellings) Regulations 2023 made changes to the Building Regulations 2018 to coordinate the approval processes to build a small second home.

The reforms facilitate the delivery of housing in Victoria by making a small second dwelling with a gross floor area of 60 square metres or less, exempt from requiring a planning permit in most residential and rural zones if specified requirements are met.

Analysis by the Department of Transport and Planning found there are around 700,000 lots of 300 square metres or larger eligible to have a small second home in residential zones across the state, and roughly 2,450 in rural zones – all of which have no overlays.

Research undertaken by the University of Sydney indicates this type of approach has increased the supply of secondary dwellings representing approximately 5,000 dwellings or 10 per cent of all dwelling approvals per annum.

The changes mean families and communities can stay together and connected. More people will have access to affordable housing choices in the areas they want to live, close to jobs, services, public transport, education, and healthcare. It also means we’re better equipped to adapt to the changing way we live, with smaller families and single person households becoming more common.

## Initiatives to share planning data and improve visibility of factors affecting housing delivery

The Department of Transport and Planning monitors the housing supply pipeline of development-ready land in metropolitan Melbourne’s growth areas and major infill projects through the Urban Development Program (UDP). The UDP has been produced annually since 2003.

Publicly available data and insights about the results are available on the Planning website: https://www.planning.vic.gov.au/guides-and-resources/Data-spatial-and-insights/discover-and-access-planning-open-data/urban-development-program

The Planning Permit Activity Reporting system (PPARs) has been in operation for almost 20 years. It provides monthly, quarterly and annual reporting of planning application data. The Victorian government has recently made the data more accessible through the creation of a user-friendly public facing Planning permit activity reporting dashboard. It allows the user to filter information about a particular type of planning application across either a Local Government Area (LGA) or the state, to monitor change over time.

# Measure 10 All levels of government will ensure the efficient use of government land, including the identification of surplus land suitable for housing and the delivery of best practice projects to support housing supply, diversity and affordability.

## Well located government land suitable for housing

Establishment of the Land Coordinator General

Update: Enacted | First reported in March 2024

The establishment of a new Land Coordinator General (LCG) function within the Department of Transport and Planning, ensures a ‘front-door’, clear and single-entry point into government, to coordinate significant projects across departments which meet the Victorian Government’s housing and growth policy objectives.

The LCG function enables the streamlined coordination of land, planning and precincts outcomes across government, creating a land policy environment that simplifies practices, reduces the costs and administrative burdens of land transactions, and improves priority infrastructure timeframes.

The LCG will continue to work with a range of government agencies to unlock underutilised and surplus land for housing. The unlocking of government land will increase clarity and investment certainty for private developers and institutional investors, while ensuring the provision of affordable housing targeted at very low, low and moderate income households occurs in partnership with Registered Housing Agencies or other affordable housing providers.

## Best practice examples of developing government land

Case Study – Jewell Station Precinct The Jewell Station precinct in Brunswick has been transformed into a vibrant local hub through the redevelopment of formerly underused government land. The redevelopment was led by VicTrack, and involved developing transport land around the station to deliver a new mixed-use development, as well as landscaping and station access improvements. The project has improved facilities for not only commuters but also the community, by introducing new retail spaces and areas to relax and socialise. The project embodies the idea that good design can improve wellbeing, diversity, and connection in the community, while also increasing housing supply in the inner suburbs of Melbourne. The project included: constructing two eight story mixed-use buildings, with ground floor retail and 121 one, two and three bedroom apartments building new bike parking facilities upgrading the Upfield shared user path within the precinct restoring the heritage station building to make it the centrepiece of the revamped station forecourt building new ramps and stairs to improve access to the station. - Following the redevelopment, the community can also now enjoy a garden area, outdoor performance areas, and artistic and cultural spaces within the station precinct. Residents can find a strong sense of community connection in this very dynamic urban milieu with the benefit of being close to public transport. The improvements to the station precinct were funded by VicTrack with part-proceeds from the developments delivered by Neometro. With this example set by VicTrack, there are more opportunities for development to support the increase of housing supply, particularly affordable housing. Further information: https://www.victrack.com.au/projects/completed/jewell-station-precinct

For the purpose of this report it is assumed that development ready means land with infrastructure that is ready to sell and/or construct.

Where appropriate and where such zoning and planning does not add to construction costs e.g., through the use of incentives such as density bonuses.