First Nations Economic Partnership

Access to Capital and Institutional Arrangements Working Group – Work Schedule

- This Work Schedule sets out specific Working Group activities, milestones and outputs. It focuses on immediate priorities and early opportunities. It complements the Terms of Reference, which have a broad scope to reflect the opportunities relating to access to capital and institutional arrangements. At each phase, a specific key priority area will be considered, with conclusions and recommendations captured in meeting records.

| Phase | Timeline | Key Activities | Milestones and Outputs | Responsibility |
| --- | --- | --- | --- | --- |
| Working Group arrangements and governance | Feb–Mar 2026 | - Confirm scope and priorities with reference to Terms of Reference - Confirm Secretariat function for Working Group - Finalise Work Schedule and engagement plan - Identify Members and Experts for Working Group - Partners to approve Working Group Schedule, members and timeframes (out of session) - Confirm funding arrangements with NIAA | - Early March: Work Schedule and Members/Experts agreed by Partnership - Funding approved by NIAA Phase output: A clear plan for the Working Group to start work, engage broadly and deliver tangible recommendations | - Co-Chairs |
| Phase 1: Start-up, scoping and alignment, as well as SIV advice | Mar–Apr 2026 | - The Working Group Co-Chairs will identify key priority areas, commencing with: - SIVs - the role of IBA and ILSC - opportunities for PBCs - other relevant issues identified by the Co-Chairs. - Develop options for SIVs, e.g. investment mandate changes | - Mid-March 2026: SIV Meeting - Late March 2026: Finalise early SIV Advice Note Phase outputs: 1) Timeline for progressing key priorities, including engagement schedule 2) Practical options and recommendations on SIVs | - Co-Chairs - Treasury and Department of Finance |
| Phase 2: Evidence review, mapping and initial engagement, and advice on other priority areas | May–Jun 2026 | - Assess current state and identify opportunities, including: - review of existing evidence (Murru waaruu, First Nations Economic Empowerment Working Group, inquiries etc.) - map types of capital, institutional roles, legislative impediments, stakeholders, and existing policy opportunities and levers - examine international practices and case notes - identify models to provide advice and capacity building around finance and access to capital - Explore and develop options for the next key priority area(s) | - May 2026: Foundational Issues Paper; briefing to Economic Partnership Phase outputs: 1) Initial Phase 2 assessment findings 2) Next set of options and recommendations on key priority area(s) (based on Phase 1) | - Co-Chairs - Alliance, with Government input |
| Phase 3: Options to accelerate access to capital and markets, including a Finance and Investment Council and Institutional reforms | Jun–Aug 2026 6-month Interim Report due | - Drawing on Phase 2 and consultation with key stakeholders (e.g. targeted engagements, sector roundtables etc.), finalise the Interim Report that includes reform options to: - accelerate the growth and long-term sustainability of First Nations businesses - improve access to domestic and international markets, affordable capital, tailored investment support - maximise institutional settings, including exploring the roles of a potential investment and finance council, institutional investors (e.g. banks, super funds etc.) and institutional reforms. | - July 2026: Finalise Interim Report - Draft content for Economic Framework Phase outputs: 1) Specific options and recommendations 2) Interim Report | - Co-Chairs - Alliance to lead drafting of Interim Report, with Government input Inputs into Interim Report (from Government/ Alliance/ others) to be agreed by the Co-Chairs and contributors. |
| Phase 4: Co-design of preferred package and Framework integration | Sep – Oct 2026 | - Refine options into preferred reform package (options could include an investment and finance council, capital mechanisms, institutional changes) - Circulate Options and Package Paper, validation roundtables - Develop MYEFO proposal for consideration by Government | - Oct 2026: Draft MYEFO proposal completed Phase outputs: 1) Specific options 2) Draft MYEFO proposal | - Co-Chairs |
| Phase 5: Post-Framework finalisation and early implementation support | Nov 2026 – Jan 2027 12-month Final Report due | - Finalise report and ensure alignment with First Nations Economic Framework - Develop recommendations for implementation of agreed policy options - Co-chairs develop business case for Working Group extension | - Dec 2026: Final Report of advice and recommendations from Working Group - Dec 2026: seek agreement to extend Working Group Phase outputs: 1) Final Report 2) Specific recommendations on implementation | - Co-Chairs - Alliance to lead drafting of Final Report, with Government input Inputs into Final Report to be agreed by the Co-Chairs and contributors. |
| Phase 6: Next steps: Consolidation, monitoring and extended handover | Jan–March 2027 | - Develop agreed implementation plan / roadmap and handover briefings - Capture feedback and refine guidance based on lessons learned during 2026 - Co-Chairs to consider recommendations on how key learnings and reflections from Working Group could inform Partnership Work going forwards. | - Jan-Feb 2027: Consideration of next steps - March 2027: Preliminary evaluation and assessment Phase output: Summary of lessons learned | - Co-Chairs |