First Nations Economic Partnership

2026–27 Annual Workplan

(1 July to 31 December 2026)

About the First Nations Economic Partnership (Economic Partnership)

- The Economic Partnership has been established to advance the economic empowerment and lasting economic security of First Nations peoples, communities and organisations.

- The Economic Partnership establishes a mechanism for the Partners to share in decisions about reforms to First Nations economic policy, built around the ‘strong partnership elements’ of Priority Reform One of the Closing the Gap Agreement.

- The Partners’ commitment to work together is set out in the Economic Partnership Agreement (published online).

About this Annual Workplan (Workplan)

- The Partners have agreed to develop and publish a Workplan (Partnership Agreement, clauses 36–38).

- This Workplan covers the period from 1 July 2026 to 31 December 2026.

- This Workplan will be reviewed and updated at each meeting of the Economic Partnership.

- The Workplan will be made publicly available.

Objectives – 2026-27

- The Partnership’s objectives for the period of this Workplan are to:

  - Develop policy options and initiatives for Government consideration, aligned with immediate priorities set out in the Workplan — including providing recommendations on practical policy options.

  - Establish inclusive engagement mechanisms with First Nations communities, Aboriginal and Torres Strait Islander community-controlled organisations, businesses and enterprises, Chambers of Commerce, experts, and stakeholders nationwide, consistent with the Partnership Agreement provisions on Additional Participation (clauses 23–26).

  - coordinate effectively with other partnerships and bodies to complement engagement efforts and support cross-government and cross-policy collaboration.

Deliverables – 2026-27

- The Partners agreed to focus on progressing immediate priorities for First Nations economic empowerment, as immediate actions (Partnership Agreement clauses 31–34). This Workplan sets out initial steps and initial deliverables for these areas of work. Many of these areas of work will continue in future years, building on these initial deliverables.

Revision History

| Version | Date | Author | Approved by | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 22 July 2026 | NIAA | Economic Partnership |  |

Key deliverables for 2026-27

| - Priority | - Deliverables | - Actions | - Timeframe | - Lead |
| --- | --- | --- | --- | --- |
| - 1. Annual Workplan - Clause: 32 | - Annual Workplan | - Agree 2026-27 Workplan - (1 July to 31 December 2026) | 22 July 2026 | Operational Committee, Working Groups Partners to endorse |
|  |  | - Agree 2026-27 Workplan - (1 January to 30 June 2027) | November 2026 | Operational Committee, Working Groups Partners to endorse (out-of-session) |
| - 2. First Nations Economic Framework - Clause: 33 | The Economic Partnership will, as a first priority, design an inclusive and transparent approach to developing the Economic Framework. This approach will include the development of a discussion paper and involve deep engagement with First Nations people and organisations and mainstream financial institutions and businesses. The approach will be made public and include a timeline for completion of the Economic Framework. | The Economic Partnership will, as a first priority, design an inclusive and transparent approach to developing the Economic Framework. | - 22 July 2026 | - Economic Framework Steering Committee - Partners to endorse |
|  |  | - Economic Framework Discussion Paper delivered to the Economic Partnership | - 14 September 2026 | - Economic Framework Steering Committee - Partners to endorse |
|  |  | - Draft Economic Framework | - 14 December 2026 | - Economic Framework Steering Committee - Partners to provide feedback |
|  |  | - Final Framework | - 15 January 2027 | - Economic Framework Steering Committee - Partners to endorse |
| 3. Advice on strengthening (SIVs role) Clause: 34 (a) - Detailed milestones have been agreed in the ACIA Working Group Work Schedule | Explore strengthening the role of Specialist Investment Vehicles (SIVs) in supporting improved First Nations access to capital, including consideration of investment mandates. In developing advice, the Working Group will consider work underway across Government of SIVs. | - Access to Capital and Institutional Arrangements Working Group Final Report | - 31 December 2026 | - Access to Capital and Institutional Arrangements Working Group - Partners to endorse |
| 4. Explore establishing a First Nations investment and finance council - Clause: 34 (a) - Detailed milestones have been agreed in the ACIA Working Group Work Schedule | Explore establishing a First Nations investment and finance council Work may include considering SIVs, the roles of IBA and ILSC, and private capital, building on existing programs and approaches. | - Access to Capital and Institutional Arrangements Working Group Interim Report | - 22 July 2026 | - Access to Capital and Institutional Arrangements Working Group - Partners to endorse |
|  |  | - Access to Capital and Institutional Arrangements Working Group Final Report | - 31 December 2026 | - Access to Capital and Institutional Arrangements Working Group - Partners to endorse |
| 5. Explore development of Economic Inclusion Zones - Clause: 34 (d) - Detailed milestones have been agreed in the ECP Working Group Work Schedule | Explore establishing Economic Inclusion Zones led by local First Nations organisations to develop and implement employment, education and training initiatives; identify and remove systemic policy and program barriers; deploy flexible and pooled funding; and strengthen economic participation in sectors such as the care economy, infrastructure and maintenance, cultural enterprises, and land and water management. | Employment and Career Pathways Working Group Initial Report: Exploring development of Economic Inclusion Zones | - 22 July 2026 | - Employment and Career Pathways Working Group - Partners to provide feedback |
|  |  | Employment and Career Pathways Working Group Final Report: Exploring development of Economic Inclusion Zones | - 2 December 2026 | - Employment and Career Pathways Working Group - Partners to endorse |
| - 6. Explore approaches to grow secure employment and career pathways in community-controlled sector and support capacity building - Clause 34 (e) Detailed milestones to be agreed in the Working Group Work Schedule | Through new or existing measures, design funded programs to grow secure employment and career pathways for First Nations people in the Aboriginal and Torres Strait Islander community-controlled sector, supporting transitions from unemployment, achieving wage parity, creating new job streams, investing in professional development, and prioritising community-led service delivery in emerging local economies, including the care economy | Employment and Careers Pathways Working Group Report: Exploring approaches to grow secure employment and career pathways | - 23 September 2026 | - Employment and Career Pathways Working Group - Partners to endorse |
| 7. Indigenous Procurement Policy (IPP) Clause: 34 (f) | Strengthening the outcomes and accountability of the Commonwealth’s Indigenous Procurement Policy (IPP), including implementation of the agreed recommendations from the June 2025 Australian National Audit Office report Targets for Minimum Indigenous Employment or Supply Use in Major Australian Government Procurements—Follow-up | NIAA to bring a further paper on the IPP for discussion on approach to further strengthen outcomes and accountability | - 23 September 2026 | - NIAA |
| 8. Data Policy Partnership | Support capacity building within First Nations organisations through improved data governance practices in line with Indigenous data sovereignty Partners to consider intersection of this focus with other priorities, including with Working Groups. Work with the Data Policy Partnership, and Indigenous Businesses Australia’s (IBA) Office of the Indigenous Economy, including to consider the issue of data sovereignty. | Data Policy Partnership to provide update to Partners | - 2 December 2026 | - Data Policy Partnership - All Partners to provide advice on proposed approach. |

Performance measures

Performance against these measures will be reported on a quarterly basis, at the Partnership meeting following the end of each quarter.

| Measure | Target |
| --- | --- |
| Annual Workplan published | Publication |
| Approach to developing the Economic Framework published | Publication |
| Funding allocations published | 100% of allocations |
| Meeting outcomes published 15 business days after each meeting | 100% of meetings |
| Annual written update delivered to the Accountable Ministers by 31 July 2026 | Delivery |
| Annual written update published within 5 business days of being accepted by the Accountable Ministers | Publication |
| Monitoring and evaluation framework delivered and published by 30 June 2026 | Publication |